## Slide 1: Software Engineering COMP 201
Lecturer: Sebastian Coope
Ashton Building, Room G.18
E-mail: coopes@liverpool.ac.uk
COMP 201 web-page:
http://www.csc.liv.ac.uk/~coopes/comp201
Software Cost Estimation

## Slide 2: Software Cost Estimation
Software cost estimation involves predicting the resources required for a software development process

## Slide 3: Fundamental Estimation Questions
How much effort is required to complete an activity?
How much calendar time is needed to complete an activity?
What is the total cost of an activity?
Project estimation and scheduling and interleaved management activities

## Slide 4: Software Cost Components
Hardware and software costs
Travel and training costs
Effort costs (the dominant factor in most projects)
  salaries of engineers involved in the project
  Social and insurance costs
Effort costs must take overheads into account
  costs of building, heating, lighting
  costs of networking and communications
  costs of shared facilities (e.g library, staff restaurant, etc.)

## Slide 5: Costing and Pricing
Estimates are made to discover the cost, to the developer, of producing a software system
There is not a simple relationship between the development cost and the price charged to the customer
Broader organisational, economic, political and business considerations influence the price charged

## Slide 6: Software Pricing Factors

## Slide 7: Programmer Productivity
A measure of the rate at which individual engineers involved in software development produce software and associated documentation
Not quality-oriented although quality assurance is a factor in productivity assessment
Essentially, we want to measure useful functionality produced per time unit

## Slide 8: Productivity Measures
Size-related measures based on some output from the software process. This may be lines of delivered source code, object code instructions, etc.
Function-related measures based on an estimate of the functionality of the delivered software. Function-points are the best known of this type of measure

## Slide 9: Measurement Problems
Estimating the size of the measure
Estimating the total number of programmer months which have elapsed
Estimating contractor productivity (e.g. documentation team) and incorporating this estimate in overall estimate

## Slide 10: Lines of Code
What's a line of code?
  The measure was first proposed when programs were typed on cards with one line per card
  How does this correspond to statements as in Java which can span several lines or where there can be several statements on one line
What programs should be counted as part of the system?
Assumes linear relationship between system size and volume of documentation

## Slide 11: Productivity Comparisons
The lower level the language, the more productive the programmer
  The same functionality takes more code to implement in a lower-level language than in a high-level language

## Slide 12: High and Low Level Languages

## Slide 13: Function Points
Based on a combination of program characteristics
  external inputs and outputs
  user interactions
  external interfaces
  files used by the system
A weight is associated with each of these
The function point count is computed by multiplying each raw count by the weight and summing all values

## Slide 14: Object Points
Object points are an alternative function-related measure to function points
Object points are NOT the same as object classes
The number of object points in a program is a weighted estimate of
  The number of separate screens that are displayed
  The number of reports that are produced by the system
  The number of modules that must be developed

## Slide 15: Productivity Estimates
Real-time embedded systems, 40-160 LOC/P-month
Systems programs , 150-400 LOC/P-month
Commercial applications, 200-800 LOC/P-month
In object points, productivity has been measured between 4 and 50 object points/month depending on type of application, tool support and developer capability

## Slide 16: Factors Affecting Productivity

## Slide 17: Quality and Productivity
It could be argued that all metrics based on volume/unit time are flawed because they do not take quality into account
Productivity may generally be increased at the cost of quality
It is not clear how productivity/quality metrics are related
If change is constant (simplifying and improving code for example) then an approach based on counting lines of code is not meaningful

## Slide 18: Estimation Techniques
There is no simple way to make an accurate estimate of the effort required to develop a software system
  Initial estimates are based on inadequate information in a user requirements definition
  The software may run on unfamiliar computers or use new technology
  The people in the project may be unknown
Project cost estimates may be self-fulfilling
  The estimate defines the budget and the product is adjusted to meet the budget

## Slide 19: Estimation Techniques
Algorithmic cost modelling
Expert judgement
Estimation by analogy
Parkinson's Law
Pricing to win

## Slide 20: Algorithmic Code Modelling
A formulaic approach based on historical cost information and which is generally based on the size of the software
Discussed later …

## Slide 21: Expert Judgement
One or more experts in both software development and the application domain use their experience to predict software costs. Process iterates until some consensus is reached.
Advantages: Relatively cheap estimation method. Can be accurate if experts have direct experience of similar systems
Disadvantages: Very inaccurate if there are no experts!

## Slide 22: Estimation by Analogy
The cost of a project is computed by comparing the project to a similar project in the same application domain
Advantages: Accurate if project data available
Disadvantages: Impossible if no comparable project has been tackled. Needs systematically maintained cost database

## Slide 23: Parkinson's Law
The project costs whatever resources are available
Advantages: No overspend
Disadvantages: System is usually unfinished
Parkinson’s Law states that work expands to fill the time available. The cost is determined by available resources rather than by objective statement.
Example: Project should be delivered in 12 months and 5 people are available. Effort = 60 p/m

## Slide 24: Pricing to Win
The project costs whatever the customer has to spend on it
Advantages: You get the contract
Disadvantages: The probability that the customer gets the system he or she wants is small. Costs do not accurately reflect the work required

## Slide 25: Top-Down and Bottom-Up Estimation
Any of these approaches may be used top-down or bottom-up
Top-down
  Start at the system level and assess the overall system functionality and how this is delivered through sub-systems
Bottom-up
  Start at the component level and estimate the effort required for each component. Add these efforts to reach a final estimate

## Slide 26: Estimation Methods
Each method has strengths and weaknesses
Estimation should be based on several methods
If these do not return approximately the same result, there is insufficient information available
Some action should be taken to find out more in order to make more accurate estimates
Pricing to win is sometimes the only applicable method

## Slide 27: Experience-Based Estimates
Estimating is primarily experience-based
However, new methods and technologies may make estimating based on experience inaccurate
  Object-oriented rather than function-oriented development
  Client-server systems rather than mainframe systems
  Off the shelf components
  Component-based software engineering
  CASE tools and program generators

## Slide 28: Pricing to Win
This approach may seem unethical and unbusinesslike?
However, when detailed information is lacking it may be the only appropriate strategy
The project cost is agreed on the basis of an outline proposal and the development is constrained by that cost
A detailed specification may be negotiated or an evolutionary approach used for system development

## Slide 29: Algorithmic Cost Modelling
Cost is estimated as a mathematical function of product, project and process attributes whose values are estimated by project managers
  Effort = A ´ SizeB ´ M
  A is an organisation-dependent constant, B reflects the disproportionate effort for large projects and M is a multiplier reflecting product, process and people attributes
Most commonly used product attribute for cost estimation is code size
Most models are basically similar but with different values for A, B and M

## Slide 30: Estimation Accuracy
The size of a software system can only be known accurately when it is finished
Several factors influence the final size
  Use of COTS and components
  Programming language
  Distribution of system
As the development process progresses then the size estimate becomes more accurate